## Slide 1
Software Estimation

## Slide 2: Heuristic Estimation Techniques
Single Variable Model:
  Parameter to be Estimated=c1*ed1
Multivariable Model:
  Assumes that the parameter to be estimated depends on more than one characteristic.
    Parameter to be Estimated=c1*ed1 + c2*ed2 + c3*ed3 ......
  Usually more accurate than single variable models.

## Slide 3: COCOMO Model
COCOMO (COnstructive COst MOdel) proposed by Boehm.
Divides software product developments into 3 categories:
  Organic
  Semidetached
  Embedded

## Slide 4: COCOMO Product classes
Roughly correspond to:
  application, utility and system programs respectively.
    Data processing and scientific programs are considered to be application programs.
    Compilers, linkers, editors, etc., are utility programs.
    Operating systems and real-time system programs, etc. are system programs.

## Slide 5: Elaboration of Product classes
Organic:
  Relatively small groups
    working to develop well-understood applications.
Semidetached:
  Project team consists of a mixture of experienced and inexperienced staff.
Embedded:
  The software is strongly coupled to complex hardware, or real-time systems.

## Slide 6: COCOMO Model (CONT.)
For each of the three product categories:
  From size estimation (in KLOC), Boehm provides equations to predict:
    project duration in months
    effort in programmer-months
Boehm obtained these equations:
  examined historical data collected from a large number of actual projects.

## Slide 7: COCOMO Model (CONT.)
Software cost estimation is done through three stages:
  Basic COCOMO,
  Intermediate COCOMO,
  Complete COCOMO.

## Slide 8: Basic COCOMO Model (CONT.)
Gives only an approximate estimation:
  Effort = a1*(KLOC)a2
  Tdev = b1 (Effort)b2
    KLOC is the estimated kilo lines of source code,
    a1,a2,b1,b2 are constants for different categories of software products,
    Tdev is the estimated time to develop the software in months,
    Effort estimation is obtained in terms of person months (PMs).

## Slide 9: Development Effort Estimation
Organic :
  Effort = 2.4*(KLOC)1.05 PM
Semi-detached:
  Effort = 3.0*(KLOC)1.12 PM
Embedded:
  Effort = 3.6*(KLOC)1.20PM

## Slide 10: Development Time Estimation
Organic:
  Tdev = 2.5*(Effort)0.38 Months
Semi-detached:
  Tdev = 2.5*(Effort)0.35 Months
Embedded:
  Tdev = 2.5*(Effort)0.32 Months

## Slide 11: Basic COCOMO Model (CONT.)
Effort is somewhat super-linear in problem size.
Effort
Size
Embedded
Semidetached
Organic

## Slide 12: Basic COCOMO Model (CONT.)
Development time
  sublinear function of product size.
When product size increases two times,
  development time does not double.
Time taken:
  almost same for all the three product categories.
Size
Dev. Time
Embedded
Semidetached
Organic
60K
18 Months
14 Months
30K

## Slide 13: Basic COCOMO Model (CONT.)
Development time does not increase linearly with product size:
  For larger products more parallel activities can be identified:
    can be carried out simultaneously by a number of engineers.

## Slide 14: Basic COCOMO Model (CONT.)
Development time is roughly the same for all the three categories of products:
  For example, a 60 KLOC program can be developed in approximately 18 months
    regardless of whether it is of organic, semi-detached, or embedded type.
  There is more scope for parallel activities for system and utility programs,
    than application programs.

## Slide 15: Example
The size of an organic software product has been estimated to be 32,000 lines of source code.
Effort = 2.4*(32)1.05 = 91 PM
Nominal development time = 2.5*(91)0.38 = 14 months