## Slide 1
Software Estimation

## Slide 2: Intermediate COCOMO
Extension of Basic COCOMO
Why Use ?
Basic model lacks accuracy
Computes software development effort as a function of program size and set of 15 Cost Drivers
Cost Driver: A multiplicative factor that determines the effort required to complete the software project.
Why Cost Drivers?
Adjust the nominal cost of a project to the actual project Environment.
For each Characteristics, Estimator decides the scale factor
Very Low
Low
Nominal
High
Very High
Extra High

## Slide 3: Cost Drivers
Product Attributes
Required Software Reliability (RELY)
Personnel Attributes
Analyst Capability (ACAP)
Application Experience (AEXP)
Database Size (DATA)
Project Attributes
Modern programming practices (MODP)
Use of Software tools (TOOL)
Computer turnaround time (TURN)
Execution Time Constraint (TIME)
Computer Attributes
Product Complexity (CPLX)
Main Storage constraint (STOR)
Virtual Machine volatility (VIRT)
Programmer Capability (PCAP)
Virtual Machine Experience (VEXP)
Programming language Experience (LEXP)
Required development schedule (SCED)

## Slide 4: The Calculation
Multiply all 15 Cost Drivers to get Effort Adjustment Factor(EAF)
E(Effort) = a1*(KLOC)a2 * EAF(in Person-Month)
D(Development Time) = b1*(E)b2 (in month)
SS (Avg Staff Size) = E/D (in persons)
P (Productivity) = KLOC/E (in KLOC/Person-month)
Project | a1 | a2 | b1 | b2
Organic | 3.2 | 1.05 | 2.5 | 0.38
Semidetached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 2.8 | 1.20 | 2.5 | 0.32

## Slide 5
Effort Adjustment Factor
Cost Driver
Very
Low
Low
Nominal
High
Very
High
Extra
High
Required Reliability
.75
.88
1.00
1.15
1.40
1.40
Database Size
.94
.94
1.00
1.08
1.16
1.16
Product Complexity
.70
.85
1.00
1.15
1.30
1.65
Execution Time Constraint
1.00
1.00
1.00
1.11
1.30
1.66
Main Storage Constraint
1.00
1.00
1.00
1.06
1.21
1.56
Virtual Machine Volatility
.87
.87
1.00
1.15
1.30
1.30
Comp Turn Around Time
.87
.87
1.00
1.07
1.15
1.15
Analyst Capability
1.46
1.19
1.00
.86
.71
.71
Application Experience
1.29
1.13
1.00
.91
.82
.82
Programmers Capability
1.42
1.17
1.00
.86
.70
.70
Virtual machine Experience
1.21
1.10
1.00
.90
.90
.90
Language Experience
1.14
1.07
1.00
.95
.95
.95
Modern Prog Practices
1.24
1.10
1.00
.91
.82
.82
SW Tools
1.24
1.10
1.00
.91
.83
.83
Required Dev Schedule
1.23
1.08
1.00
1.04
1.10
1,10

## Slide 6: Intermediate COCOMO : Example
A new project with estimated 400 KLOC embedded system has to be developed. Project manager hires developers of very low quality in application experience but a high experience in programming language. Calculate the Effort, Development time, Staff size & Productivity.
Cost Drivers | Very Low | Low | Nominal | High | Very High | Extra High
AEXP | 1.29 | 1.13 | 1.00 | 0.91 | 0.82 | --
LEXP | 1.14 | 1.07 | 1.00 | 0.95 | -- | --

## Slide 7: Example (Contd.)
EAF = 1.29 * 0.95 = 1.22
400 KLOC Embedded System
Effort = 2.8*(400)1.20 * 1.22 = 3712 * 1.22 = 4528 person-months
Development Time = 2.5 * (4528)0.32 = 2.5 * 14.78 = 36.9 months
Avg. Staff Size = E/D = 4528/36.9 = 122 persons
Productivity = KLOC/Effort = 400/4528 = 0.0884 KLOC/person-month

## Slide 8: Complete COCOMO
Detailed COCOMO = Intermediate COCOMO + assessment of Cost Drivers impact on each phase.
Phases
  Plans and requirements
  System Design
  Detailed Design
  Module code and test
  Integrate and test
Cost of each subsystem is estimated separately. This reduces the margin of error.

## Slide 9: The Calculation
Multiply all 15 Cost Drivers to get Effort Adjustment Factor(EAF)
E(Effort) = a1(KLOC)a2 * EAF(in Person-Month)
D(Development Time) = b1(E)b2 (in month)
Ep (Effort in Phase) = µp * E (in Person-Month)
Dp (Development Time of Phase) = τp * D (in month)
µp , τp Phase sensitive multipliers

## Slide 10: Detailed COCOMO : Example
  Consider a oraganic project to develop a full screen editor. The major components identified and their sizes are (i) Screen Edit – 4K (ii) Command Lang Interpreter – 2K (iii) File Input and Output – 1K (iv) Cursor movement – 2K (v) Screen Movement – 3K. Assume the Required software reliability is high, product complexity is high, analyst capability is high & programming language experience is low. Use COCOMO model to estimate cost and time for different phases.
  Phase value of µp and τp
Cost Drivers | Very Low | Low | Nominal | High | Very High | Extra High
RELY | 0.75 | 0.88 | 1.00 | 1.15 | 1.40 | --
CPLX | 0.70 | 0.85 | 1.00 | 1.15 | 1.30 | 1.65
ACAP | 1.46 | 1.19 | 1.00 | 0.86 | 0.71 | 
LEXP | 1.14 | 1.07 | 1.00 | 0.95 | -- | --
 | Plan & Reqr | System Design | Detail Design | Module code & test | Integration & Test
Organic Small µp | 0.06 | 0.16 | 0.26 | 0.42 | 0.16
Organic Small τp | 0.10 | 0.19 | 0.24 | 0.39 | 0.18

## Slide 11
  Size of modules : 4 + 2 + 1 + 2 + 3 = 12 KLOC [Organic]
  EAF = 1.15 * 1.15 * 0.86 * 1.07 = 1.2169
  Initial Effort (E) = ab(KLOC)bb * EAF = 3.2*(12)1.05 * 1.2169 = 52.9 person-months
  Initial Development Time = cb(E)db =2.5*(52.9)0.38 = 11.29 months
Example (Contd.)

## Slide 12: Example (Contd.)
  Phase wise effort & development time distribution
 | E | D | Ep (in person-months) | Dp (in months)
Plan & Requirement | 52.9 | 11.29 | 0.06*52.9 = 3.17 | 0.10*11.29=1.12
System Design | 52.9 | 11.29 | 0.16*52.9=8.46 | 0.19*11.29=2.14
Detail Design | 52.9 | 11.29 | 0.26*52.9=13.74 | 0.24*11.29=2.70
Module code & test | 52.9 | 11.29 | 0.42*52.9=22.21 | 0.39*11.29=4.40
Integration & test | 52.9 | 11.29 | 0.16*52.9=8.46 | 0.18*11.29=2.03
Total |  |  | 56.04 | 12.39