## Slide 1
Software Estimation-4

## Slide 2: Staffing Level Estimation
Number of personnel required during any development project:
  not constant.
Norden in 1958 analyzed many R&D projects, and observed:
  Rayleigh curve represents the number of full-time personnel required at any time.

## Slide 3: Rayleigh Curve
Rayleigh curve is specified by two parameters:
  td the time at which the curve reaches its maximum
  K the total area under the curve.
E=f(K, td)
E= (K/td2)*t*e(-t2/2td2)
Effort
Time
td
Rayleigh Curve

## Slide 4: Putnam’s Work:
In 1976, Putnam studied the problem of staffing of software projects:
  observed that the level of effort required in software development efforts has a similar to R & D.
  found that the Rayleigh-Norden curve
    relates the number of delivered lines of code to effort and development time.

## Slide 5: Putnam’s Work (CONT.):
Putnam analyzed a large number of army projects, and derived the expression:
L=CkK1/3td4/3
  K is the effort expended and L is the size in KLOC.
  td is the time to develop the software.
  Ck is the state of technology constant
    reflects factors that affect programmer productivity.

## Slide 6: Putnam’s Work (CONT.):
Ck=2 for poor development environment
  no methodology, poor documentation, and review, etc.
Ck=8 for good software development environment
  software engineering principles used
Ck=11 for an excellent environment

## Slide 7: Rayleigh Curve
Very small number of engineers are needed at the beginning of a project
  carry out planning and specification.
As the project progresses:
  more detailed work is required,
  number of engineers slowly increases and reaches a peak.

## Slide 8: Rayleigh Curve
Putnam observed that:
  the time at which the Rayleigh curve reaches its maximum value
    corresponds to system code and testing of product.
  After system testing,
    the number of project staff falls till product installation and delivery.

## Slide 9: Effect of Schedule Change on Cost
Using the Putnam's expression for L, K=L3/Ck3td4 Or, K=C1/td4
For the same product size, C1=L3/Ck3 is a constant.
Or, K1/K2 = td24/td14

## Slide 10: Effect of Schedule Change on Cost (CONT.)
Observe:
  a relatively small compression in delivery schedule
    can result in substantial penalty on human effort.
Also, observe:
  benefits can be gained by using fewer people over a somewhat longer time span.

## Slide 11: Example
If the estimated development time is 1 year, then in order to develop the product in 6 months,
  the total effort and hence the cost increases 16 times.
  In other words,
    the relationship between effort and the chronological delivery time is highly nonlinear.

## Slide 12: Effect of Schedule Change on Cost (CONT.)
Putnam model indicates extreme penalty for schedule compression
  and extreme reward for expanding the schedule.
Putnam estimation model works reasonably well for very large systems,
  but seriously overestimates the effort for medium and small systems.

## Slide 13: Effect of Schedule Change on Cost (CONT.)
Boehm observed:
  “There is a limit beyond which the schedule of a software project cannot be reduced by buying any more personnel or equipment.”
  This limit occurs roughly at 75% of the nominal time estimate.

## Slide 14: Effect of Schedule Change on Cost (CONT.)
If a project manager accepts a customer demand to compress the development time by more than 25%
  very unlikely to succeed.
    every project has only a limited amount of parallel activities
    sequential activities cannot be speeded up by hiring any number of additional engineers.
    many engineers have to sit idle.

## Slide 15: Jensen Model
Jensen model is very similar to Putnam model.
  attempts to soften the effect of schedule compression on effort
  makes it applicable to smaller and medium sized projects.

## Slide 16: Jensen Model
Jensen proposed the equation:
  L=CtetdK1/2
  Where,
    Cte is the effective technology constant,
    td is the time to develop the software, and
    K is the effort needed to develop the software.

## Slide 17: Example
Suppose you have estimated the nominal development time of moderate-sized software product to be 5 months. You have also estimated that it will cost ₹ 50,000 to develop the software product. Now, the customer comes and tells you that he wants you to accelerate the delivery time by 20%. Estimate and compare the additional cost that you would charge to customer for this accelerated delivery by Putnam’s and Jensen’s model? Irrespective of whether you take less time or more time to develop the product, you are essentially developing the same product. Why then does the effort depend on the duration over which you develop the product?