## Slide 1
Software Estimation-6

## Slide 2: Activity Network and Critical Path
Activity Network:- an activity network shows the different activities making up a project, their estimated duration and interdependencies
Critical Path:- the longest way from start to finish

## Slide 3: Elements of activity network
Minimum Time (MT):- the time to complete the project is the maximum of all paths from start to finish
Earliest Start (ES):- the earliest time to start an activity, given that prior activities must be completed first. It is the maximum of all paths from start to this activity
Earliest Finish (EF):- the earliest finish time is the sum ES and the duration of activity
Latest Start (LS):- the latest start time of an activity is the time at which the activity must be start without delaying the project. It is the difference between MT and maximum of all paths from this task to finish.
Latest Finish (LF):- the latest finish time of an activity is the time at which the activity must be completed without delaying the project. It can be obtained by adding duration of activity to LS.
Slack Time (ST):- the slack time it the total time that an activity may be delayed without affecting the end time of project. It can be obtained by LF-EF or LS-ES

## Slide 4: Example
S. No. | Activity ID | Duration | Dependency | ES | EF | LS | LF | ST
1 | A | 15 |  |  |  |  |  | 
2 | B | 45 | A |  |  |  |  | 
3 | C | 30 | A |  |  |  |  | 
4 | D | 105 | B |  |  |  |  | 
5 | E | 45 | C |  |  |  |  | 
6 | F | 120 | D,E |  |  |  |  | 
7 | G | 60 | A |  |  |  |  | 

## Slide 5
S. No. | Activity ID | Duration | Dependency
1 | A | 15 | 
2 | B | 45 | A
3 | C | 30 | A
4 | D | 105 | B
5 | E | 45 | C
6 | F | 120 | D,E
7 | G | 60 | A

## Slide 6: Calculations of elements
S. No. | Activity ID | Duration | Dependency | ES | EF | LS | LF | ST
1 | A | 15 |  |  |  |  |  | 
2 | B | 45 | A |  |  |  |  | 
3 | C | 30 | A |  |  |  |  | 
4 | D | 105 | B |  |  |  |  | 
5 | E | 45 | C |  |  |  |  | 
6 | F | 120 | D,E |  |  |  |  | 
7 | G | 60 | A |  |  |  |  | 

## Slide 7: Example 2
S. No. | Activity ID | Duration | Dependency | ES | EF | LS | LF | ST
1 | T1 | 8 |  |  |  |  |  | 
2 | T2 | 15 |  |  |  |  |  | 
3 | T3 | 15 | T1 (M1) |  |  |  |  | 
4 | T4 | 10 |  |  |  |  |  | 
5 | T5 | 10 | T2,T4 (M2) |  |  |  |  | 
6 | T6 | 5 | T1,T2 (M3) |  |  |  |  | 
7 | T7 | 20 | T1 (M1) |  |  |  |  | 
8 | T8 | 25 | T4 (M5) |  |  |  |  | 
9 | T9 | 15 | T3,T6 (M4) |  |  |  |  | 
10 | T10 | 15 | T5, T7 (M7) |  |  |  |  | 
11 | T11 | 7 | T9 (M6) |  |  |  |  | 
12 | T12 | 10 | T11 (M8) |  |  |  |  | 

## Slide 8
T12 10
T10 15
T1 8
T3 15
T2 15
T6 5
T4 10
T5 10
T11 7
T9 15
T7 20
T8 25
Start
M1
M3
M2
M4
M5
M7
M6
M8
End